## Slide 1: VAPT Project Annual Plan for 50 Apps

## Slide 2: Summary of Plan
Application inventory finalization
Risk ranking (Critical/High/Medium/Low)
Prioritization of apps
Stakeholder onboarding
Define tooling (Burp, Nessus, MobSF, ZAP, Postman, etc.)
Establish reporting templates & SLAs
Set up communication channels (Jira/ServiceNow for tracking)
Weekly progress reviews

## Slide 3: Annual Project Plan – 50 Apps VAPT in 1 Year
1. High-Level Targets
Total apps: 50
Project duration: 12 months
Average apps per month: ~4–5
VAPT time per app:
  Web/API: 1–2 weeks
  Mobile: 2–3 weeks
  Thick client: 3 weeks
Team required: 2–4 security engineers (depending on complexity)

## Slide 4: Project Phases (Annual Plan)
Phase 1 — Initiation (Month 1)
Deliverables:
Application inventory finalization
Risk ranking (Critical/High/Medium/Low)
Prioritization of apps
Stakeholder onboarding
Define tooling (Burp, Nessus, MobSF, ZAP, Postman, etc.)
Establish reporting templates & SLAs

## Slide 5: Quarterly Execution Plan (4 Quarters)
Q1 (Months 1–3) — Foundation + First 12 Apps
Target: 12 apps Breakdown: 4 apps/month Activities:
Set up communication channels (Jira/ServiceNow for tracking)
Begin VAPT on first batch
Weekly progress reviews
Start retests for apps from Month 1

## Slide 6: Q2 (Months 4–6) — Full Execution Mode (13 Apps)
Target: 13 apps Breakdown: ~4–5 apps/month Activities:
Continue testing pipeline
Optimize automation (SAST/DAST + scripts)
Perform mid-year risk assessment
Ensure remediation verification cycle is smooth

## Slide 7: Q3 (Months 7–9) — Peak Productivity (13 Apps)
Target: 13 apps Breakdown: ~4–5 apps/month Activities:
Parallel testing streams
Prioritize high-risk apps
Do penetration tests before major releases
Monthly CISO reporting
Retests for Q2 apps

## Slide 8: Q4 (Months 10–12) — Closure + Remaining 12 Apps
Target: 12 apps Breakdown: ~4 apps/month Activities:
Complete tests for last batch
Ensure all retests completed
Prepare annual security summary
Lessons learned + improvements for next year

## Slide 9: Monthly Work Plan (Typical Month)
Outcome: 4–5 apps tested each month by running 2 streams parallel.
Week | Activities
Week 1 | Kickoff, gather test creds, enumerate scope
Week 2 | Deep testing + exploitation
Week 3 | Reporting + risk scoring
Week 4 | Developer remediation guidance + retest

## Slide 10: Team Planning
Minimum team size
2 Penetration Testers → 2 apps/month
Better: 3–4 Testers → 4–6 apps/month
With your expertise (10+ yrs) → you lead, handle complex apps, review reports
Additional roles
Reporting support
Program manager (optional but ideal)
App owners for coordination

## Slide 11: Tools & Automation
DAST/SAST
  Burp Suite Pro
  ZAP
  Nessus/Qualys (infra/API)
  MobSF (mobile)
Snyk/Checkmarx/GitHub CodeQL (SAST)
Automation Benefits
Reduce manual effort by ~20–30%
Faster scanning cycles
Better coverage

## Slide 12: Metrics & KPIs
KPI | Target
Vulnerabilities per app | Track trends (avg High/Critical)
SLA adherence | 95% on-time delivery
False positives | <5%
App owners satisfaction | >90%

## Slide 13: Risk Management
Blockers in credentials
Unstable test environments
Late code deployments
High app complexity
Team bandwidth

## Slide 14: Final Year-End Deliverables
50 VAPT reports
Retest reports
Dashboard of vulnerabilities
Attack surface overview
Annual security posture summary
Recommendations for next cycle